## Product Backlog Template
Product Backlog Template
Backlog Item ID | Type of Backlog Item | Description | Priority | Story Points | Status | Sprint | Assignee | Acceptance Criteria
1 | Epic | Secure Data Embedding in Java Bytecode | High | 20 | To Do | Sprint 1 | Saanvi M | System can embed encrypted payload into .class file without breaking execution.
2 | User Story | As a user, I want to provide text/file payload to be hidden in the bytecode. | High | 5 | To Do | Sprint 1 | Rohith P | System accepts text input or file upload; enforces size limits (1-10MB).
3 | Bug Fix | Handle invalid .class file uploads gracefully. | High | 3 | In Progress | Sprint 1 | Sanjana G | System rejects invalid file with clear error; no crash or partial processing
4 | Technical Improvement | Modularize class file parser for maintainability. | Medium | 8 | To Do | Sprint 1 | Sachin | Class file parsing logic is separated from encryption/UI modules.
5 | Spike | Investigate maximum custom attribute size limit in JVM spec. | Low | 5 | Completed | Sprint 2 | Saketh M | Report documents JVM limits for attribute length and padding constraints.
6 | Non-Functional Requirement | System availability of 99.5% (excluding maintenance). | Medium | 8 | To Do | Sprint 2 | Sanjana G | Uptime monitoring shows 99.5% availability over 30-day period.
1 | User Story | As a user, I want to upload a Java .class file so that I can prepare it for embedding. | High | 5 | In Progress | Sprint 2 | Saanvi M | User can upload .class file; system validates magic number and version.
2 | User Story | As an authorized user, I want to extract encrypted payload from a modified .class file. | High | 3 | In Progress | Sprint 2 | Rohith P | Modified file is downloadable immediately after embedding.
3 | User Story | As an authorized user, I want to extract encrypted payload from a modified .class file. | Medium | 2 | To Do | Sprint 3 | Rohith A | System decrypts data using KMS; original data is displayed to user.
4 | User Story | As an authorized user, I want to decrypt extracted payload to view original data. | High | 3 | To Do | Sprint 3 | Sachin | Reset email is sent successfully using the email service.
5 | Bug Fix | Fix decryption failure when embedded payload contains special characters . | Critical | 2 | Done | Sprint 3 | Saketh M | Payload with emojis, Unicode, or special characters (©, ñ, 你好) encrypts and decrypts correctly without data loss or corruption
6 | Technical Improvement | Optimize database queries for faster page load times | Medium | 5 | To Do | Sprint 3 | Sanjana G | Audit log page loads in <1 second for last 100 entries; query optimization reduces database load by 40%.
7 | Spike | Investigate maximum custom attribute size limit in JVM spec. | Low | 3 | To Do | Sprint 4 | Rohith P | Report documents JVM limits for attribute length and padding constraints.
8 | Non-Functional Requirement | Upload validation must complete within 500ms for files up to 1MB. | High | 2 | To Do | Sprint 4 | Rohith A | Validation step (magic number, version, size) takes <500ms for ≤1MB files.
Free Related Templates
Agile Sprint Plan Template
Product Roadmap Template
Task Tracker Dashboard